## Plan
Plan ID | Plan name | Date of export
nEsqMKD2RkyoemGE6e39wckAFJR6 | feature 4-Garmet_size_meserment | 2026-10-14

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
XIFciMNKgkOXgymMpHR01ckAGzrE | Define the garment size measurement research problem | Project Initiation and Research |  | Completed | Medium | JAYARATHNA W G U C G it22187796 | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
i2Nht9YbdECG7yZShYJu38kAJJ2x | Study best-frame selection and garment measurement methods | Project Initiation and Research |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
rlSzg7tO6E-d-AzMPZ93RskAOW-c | elect suitable technologies and development tools | Project Initiation and Research |  | Completed | Medium | JAYARATHNA W G U C G it22187796 | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
I2O1vd2uU0iObMfdYcYybskAK4_j | Prepare the proposed system methodology | Project Initiation and Research |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
WcomMjJzYUKCtrtHFAojK8kABrfu | Prepare the video collection environment | Video Collection and Environment Setup |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
BF6dpu2AcEyD1TdHMgcdEMkALJP1 | Record and organize garment unfolding videos | Video Collection and Environment Setup |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
3AHztKQgzU-TdxUWnJroE8kACU2m | Maintain the camera height at 120 cm | Video Collection and Environment Setup |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
CfmzhoELDkeRKimDjbQ8DMkABiVZ | Configure Python, PyTorch, OpenCV, and GPU support | Video Collection and Environment Setup |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
EIQd0tsRLk2DwZTU045uJMkAGl7H | Extract frames from all collected videos | Frame Extraction and Annotation |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
sOMyLlVnX0yMlDCtsnK4YMkANVT2 | Develop the manual annotation application | Frame Extraction and Annotation |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
aWZx4aWsX0K1qBa1jR38BMkAGqqJ | Annotate frames as READY, NOT_READY, and INVALID | Frame Extraction and Annotation |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
kOK5FndMeUWNd25nDRqErskAMGkp | Review and correct inconsistent annotations | Frame Extraction and Annotation |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
ggtnhOHlLkCdcGJ3lQIA3MkAK-Ie | Combine annotations into the final CSV file | Frame Extraction and Annotation |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
KWO1H2d1rUGEbbrMmE14nckACeg0 | Prepare the MobileNetV3 training pipeline | Baseline Image Classifier |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
T6acS1yy1UyY1pgO5gbBWckAGxyK | Train the baseline image classification model | Baseline Image Classifier |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
xK8rmiij-EKPRHjr2Mb4j8kAKYUS | Evaluate model accuracy and class performance | Baseline Image Classifier |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
_MgmPo3TuE2okSmU0-hPe8kAILb- | Select the best READY confidence threshold | Baseline Image Classifier |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
P5oQ3YqM-EqjZz2AX-TdYMkAIqlM | Save the final baseline model | Baseline Image Classifier |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
QCGoQXFLLECGLQ-vrC2ZSskAHV6g | Correct annotation and event ID errors | Failed Experiments and Corrections |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
xgRxgkvzv06sdqO7KSHj9ckADFSY | Fix model loading and missing file errors | Failed Experiments and Corrections |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
cdxSEgy9RU6SXpgXXebSPskAHoK7 | Investigate the failed temporal validation gate | Failed Experiments and Corrections |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
MlVVFKkieUqZBHWpOZ4wE8kAJnVs | Correct YOLO dataset and file-path errors | Failed Experiments and Corrections |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
aQm6_znUlkCjsYmehwuob8kAGUJv | Resolve camera, detection, and measurement issues | Failed Experiments and Corrections |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
NT5lyL4EykCofEHSvKmOJckADmdi | Combine visual and temporal model predictions | Hybrid Model Evaluation |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
wEuoJp_CtUuClLtXjC6ycskAMVgz | Test different visual and temporal weights | Hybrid Model Evaluation |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
jGnAlCZpHkiwQpoq7S3V9MkAIzh0 | Compare all model strategies | Hybrid Model Evaluation |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
fsU8qv9q_EqG0TOcqxamvMkACmdY | Select the visual-only strategy as the final method | Hybrid Model Evaluation |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
-Pq_r_VTRU2pga-mtnxVQMkAOCY4 | Connect and configure the external webcam | Live Camera Best-Frame Selection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
KYP4xGONeEmD4x7fOuCEyMkAPgYi | Implement real-time frame classification | Live Camera Best-Frame Selection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
EUWHVlaneE-7d5wSq5VckMkABMdU | Automatically capture the best READY frame | Live Camera Best-Frame Selection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
9_Te_HsChUSg7UWfv_do-MkADTGO | Prevent duplicate or incorrect frame captures | Live Camera Best-Frame Selection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
6FHGU0zlu0GQL3bHEgEoe8kAInsM | Test the system under different conditions | Live Camera Best-Frame Selection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
SZQdM-ZCfkGq_0rusJNKdMkAMHam | Develop the offline best-frame extractor | Best-Frame Extraction System |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
_afdUfPwIUmVY3cjABDWf8kAE8kY | Test best-frame extraction using recorded videos | Best-Frame Extraction System |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
oydZnImbUEWIYh6uiISjSMkAPr0c | Develop the fast manual frame-selection tool | Best-Frame Extraction System |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
u0I6rIdfCkmDkssIzIz0N8kAB4FH | Process the remaining garment videos | Best-Frame Extraction System |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
4lNBDMrRIUaTNtLZIclv28kABBkL | Save and verify selected best-frame images | Best-Frame Extraction System |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
BSYO4jQmV0KqpCRJFoPHmskAAebg | Prepare and annotate the garment dataset | YOLO Garment Detection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
MLts4swsqkGR4KuPTs84EMkAOFH_ | Train the YOLOv8 garment detection model | YOLO Garment Detection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
NhMGjPjja0Ka37nZfU6cEMkAMR9N | Test the model using sample images | YOLO Garment Detection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
sEgryjfse0CD1dLLtcbEvMkAD7Nl | Improve incorrect or inconsistent detections | YOLO Garment Detection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
jfV1ushJ006U3QQiXQN1Z8kAM8gX | Integrate YOLO with best-frame selection | YOLO Garment Detection |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
Abji7WvzrkuAlWjEhf5Gd8kAPgVn | Extract the detected garment mask or contour | Garment Pixel Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
fqAvksKMY0ySkKgPt3WIVckABp1H | Calculate garment pixel width and height | Garment Pixel Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
q9C6Vs2YDUqb580DuAUBtckAFidr | Restrict measurement to a single garment | Garment Pixel Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
o0cNii5VrE2XR4m9Mn7d88kAG5GR | Test measurements for different garment types | Garment Pixel Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
0FXol0ryaUC_nPTyT-2EPMkAORwV | Prepare the fixed camera calibration setup | Camera Calibration and Centimetre Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
1tN6VT3oYUmRJRmlWDqg_8kAACmv | Calculate pixels-per-centimetre values | Camera Calibration and Centimetre Measurement |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 | 2026-08-04 | 2026-08-04 |  | true
QP4v5JTT1kuxst8rInSpLckANJJI | Calculate pixels-per-centimetre values | Camera Calibration and Centimetre Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-31 | 2026-07-28 | 2026-07-28 |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
-B7Ptjqc20KqIezcmcdmHckAOXMQ | Calculate pixels-per-centimetre values | Camera Calibration and Centimetre Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-31 | 2026-07-21 | 2026-07-21 |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
S1bwsvuqe0WGhq52m75l9skAIdDL | Calculate pixels-per-centimetre values | Camera Calibration and Centimetre Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 | 2026-07-14 | 2026-07-14 |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
U0FeOTuWP0y_1v29d9AFi8kAH9kJ | Convert pixel measurements into centimetres | Camera Calibration and Centimetre Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
oaLDU95RcUGLGC1bpZl3dckABCq9 | Validate results using manual measurements | Camera Calibration and Centimetre Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
WPrBVsr7f0qjSgL_7rVoZMkADO_1 | Record calibration limitations and measurement errors | Camera Calibration and Centimetre Measurement |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-25 | JAYARATHNA W G U C G it22187796
iyzGpCz-ME-ENOdKUHH9z8kAE3Vk | Develop the Next.js camera interface | Frontend and System Integration |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
_TOcf6NDEkCt-vFRPbottckABCYx | Connect the frontend with the Python backend | Frontend and System Integration |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
X16tiIUffEuksTWCc6mGq8kAKHLi | Integrate best-frame selection and YOLO detection | Frontend and System Integration |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
sq9ObM8rd02mbRlG9ehZ2skAGGTz | Display garment width and height in centimetres | Frontend and System Integration |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
2IjTAeBi8Ua-hsmgtssyUskAJVbs | Test the complete system workflow | Frontend and System Integration |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  | 2026-08-06 |  | false | 2026-08-31 | JAYARATHNA W G U C G it22187796
Ozq-lFZXuEKnzLe9xNBLkMkAIw00 | Test the system using unseen videos and garments | Testing, Documentation and Finalization |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
RBLoYGbMskCFZEmQGIlBXMkAPH4U | Compare automatic and manual measurements | Testing, Documentation and Finalization |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
eUd3EfZZU0Oq7_VKOgWeuMkAIgtJ | Record results, errors, and corrective actions | Testing, Documentation and Finalization |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
gPDCKCeKFEGwyUKehIFx-MkAPSIw | Prepare the project logbook and documentation | Testing, Documentation and Finalization |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
z_qPWqLl-kWYHCVnhJHLlckAKR_H | Prepare the final demonstration and presentation | Testing, Documentation and Finalization |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-08-25 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
rRWEy_buMkypnpy71JydRMkAOcmE | Update the research paper with the final component methodology and results. | Research Documentation and Publication |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
5OuF6oAmuUu9zI08M-mcH8kAOizf | Explain best-frame selection and segmentation-based garment measurement. | Research Documentation and Publication |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
CuMJSXTDDUaS8w7M3rykxMkAH_t0 | Verify all reported results against saved experiment evidence. | Research Documentation and Publication |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
czTAI_wkxk6841VxQYJXgMkAJFaN | Record camera calibration assumptions and measurement limitations. | Research Documentation and Publication |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
yXzoYEUsTEG6LcHV95ZBO8kAGxCu | Prepare the camera-ready paper and required formatting corrections. | Research Documentation and Publication |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
UbupBtMKlEqENFL3_iEEc8kABjum | Track the conference review outcome and address reviewer feedback. | Research Documentation and Publication |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
ipsxjKJvmUW7G69qaFjp28kAKfpt | Finalize the individual thesis and check the required formatting. | Final Report and Viva |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false
hQXIcQxUFU2fUklP3rVDvMkACIuB | Update diagrams for frame selection, segmentation and measurement | Final Report and Viva |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false
iQdlUA21bEqHpDAwr5_AnskABjA6 | Prepare the final presentation with verified results | Final Report and Viva |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false
um2PRDQWp0a6_3DBz13IEMkAOmJd | Prepare the live demonstration of garment measurement and counting. | Final Report and Viva |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false
_Q0KNTgGWEOVLA6LUeU5YskAMsuk | Prepare viva answers on model selection, calibration and duplicate prevention. | Final Report and Viva |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false
RdWlbh2Rz0ifRLkMKQ6B6skAM7WQ | Assemble the logbook and component evidence pack. | Final Report and Viva |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false
CPhrvIxu9UyRn2Srh1Idq8kAGmjI | Run a full demonstration rehearsal before the viva | Final Report and Viva |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false
ChRCNfy2GkS4Bx6sKLeRVskAM92i | Record panel feedback and complete the required corrections. | Final Report and Viva |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false
wx_G2IXEt02eU-KEZoeI_skAG7eN | Obtain final supervisor approval. | Final Report and Viva |  | Not started | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false
DpLiVEcCEEytEbGEY_o2pMkABfEh | Define the website requirements for the garment measurement component. | Project Website |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
Lwsh-Cu27E27dCSDMtg9ockAAnPK | Plan the component pages and website content. | Project Website |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
2FV5Xfrq30eavB414xLqw8kALT2A | Write the research overview and objectives for best-frame selection and garment size measurement. | Project Website |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
qEDAcLETU0-KJBd7MWNO0ckAGP1o | Explain the frame-selection, segmentation, calibration and size-estimation methodology. | Project Website |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
yHTwtDNBjUyhYeCCGsBT6MkAGVaj | Add verified model evaluation and garment measurement results. | Project Website |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
yKVr4w4wd0uPimAvnvi3fskAExBl | Add component diagrams, interface screenshots and demonstration videos. | Project Website |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
JHABe6HQCE-93RfhnyjCZskAPYNH | Add report downloads, presentation materials and contributor details. | Project Website |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796
MM7ptqdhq0mhcfrdVPAHIckAHTK7 | Verify the component pages and links, and support the final website deployment and submission. | Project Website |  | Completed | Medium |  | JAYARATHNA W G U C G it22187796 | 2026-10-14 |  |  |  | false | 2026-10-14 | JAYARATHNA W G U C G it22187796

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
XIFciMNKgkOXgymMpHR01ckAGzrE | Define the garment size measurement research problem | fruVw4iDokmybfAdDYQUGMkAMSOy |  | Completed | Medium | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
i2Nht9YbdECG7yZShYJu38kAJJ2x | Study best-frame selection and garment measurement methods | fruVw4iDokmybfAdDYQUGMkAMSOy |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
rlSzg7tO6E-d-AzMPZ93RskAOW-c | elect suitable technologies and development tools | fruVw4iDokmybfAdDYQUGMkAMSOy |  | Completed | Medium | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
I2O1vd2uU0iObMfdYcYybskAK4_j | Prepare the proposed system methodology | fruVw4iDokmybfAdDYQUGMkAMSOy |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
WcomMjJzYUKCtrtHFAojK8kABrfu | Prepare the video collection environment | BNVOc3FTAUmNvoy3KMkYkMkAMIc0 |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
BF6dpu2AcEyD1TdHMgcdEMkALJP1 | Record and organize garment unfolding videos | BNVOc3FTAUmNvoy3KMkYkMkAMIc0 |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
3AHztKQgzU-TdxUWnJroE8kACU2m | Maintain the camera height at 120 cm | BNVOc3FTAUmNvoy3KMkYkMkAMIc0 |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
CfmzhoELDkeRKimDjbQ8DMkABiVZ | Configure Python, PyTorch, OpenCV, and GPU support | BNVOc3FTAUmNvoy3KMkYkMkAMIc0 |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
EIQd0tsRLk2DwZTU045uJMkAGl7H | Extract frames from all collected videos | 6X9EKxG4pkukMbx5pgSqWckAATLr |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
sOMyLlVnX0yMlDCtsnK4YMkANVT2 | Develop the manual annotation application | 6X9EKxG4pkukMbx5pgSqWckAATLr |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
aWZx4aWsX0K1qBa1jR38BMkAGqqJ | Annotate frames as READY, NOT_READY, and INVALID | 6X9EKxG4pkukMbx5pgSqWckAATLr |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
kOK5FndMeUWNd25nDRqErskAMGkp | Review and correct inconsistent annotations | 6X9EKxG4pkukMbx5pgSqWckAATLr |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
ggtnhOHlLkCdcGJ3lQIA3MkAK-Ie | Combine annotations into the final CSV file | 6X9EKxG4pkukMbx5pgSqWckAATLr |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
KWO1H2d1rUGEbbrMmE14nckACeg0 | Prepare the MobileNetV3 training pipeline | v7nlmZ8DgUWgsGoBM7Jk0ckALUdj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
T6acS1yy1UyY1pgO5gbBWckAGxyK | Train the baseline image classification model | v7nlmZ8DgUWgsGoBM7Jk0ckALUdj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
xK8rmiij-EKPRHjr2Mb4j8kAKYUS | Evaluate model accuracy and class performance | v7nlmZ8DgUWgsGoBM7Jk0ckALUdj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
_MgmPo3TuE2okSmU0-hPe8kAILb- | Select the best READY confidence threshold | v7nlmZ8DgUWgsGoBM7Jk0ckALUdj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
P5oQ3YqM-EqjZz2AX-TdYMkAIqlM | Save the final baseline model | v7nlmZ8DgUWgsGoBM7Jk0ckALUdj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
QCGoQXFLLECGLQ-vrC2ZSskAHV6g | Correct annotation and event ID errors | jbwNdsAUb0CymkpYS5Kdj8kAK4uE |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
xgRxgkvzv06sdqO7KSHj9ckADFSY | Fix model loading and missing file errors | jbwNdsAUb0CymkpYS5Kdj8kAK4uE |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
cdxSEgy9RU6SXpgXXebSPskAHoK7 | Investigate the failed temporal validation gate | jbwNdsAUb0CymkpYS5Kdj8kAK4uE |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
MlVVFKkieUqZBHWpOZ4wE8kAJnVs | Correct YOLO dataset and file-path errors | jbwNdsAUb0CymkpYS5Kdj8kAK4uE |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
aQm6_znUlkCjsYmehwuob8kAGUJv | Resolve camera, detection, and measurement issues | jbwNdsAUb0CymkpYS5Kdj8kAK4uE |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
NT5lyL4EykCofEHSvKmOJckADmdi | Combine visual and temporal model predictions | X7GIIaR5ck2MlhNCA3ZM5ckAJpLi |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
wEuoJp_CtUuClLtXjC6ycskAMVgz | Test different visual and temporal weights | X7GIIaR5ck2MlhNCA3ZM5ckAJpLi |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
jGnAlCZpHkiwQpoq7S3V9MkAIzh0 | Compare all model strategies | X7GIIaR5ck2MlhNCA3ZM5ckAJpLi |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
fsU8qv9q_EqG0TOcqxamvMkACmdY | Select the visual-only strategy as the final method | X7GIIaR5ck2MlhNCA3ZM5ckAJpLi |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
-Pq_r_VTRU2pga-mtnxVQMkAOCY4 | Connect and configure the external webcam | GaeU39aVo02Ns60xX1HO8skAIPF9 |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
KYP4xGONeEmD4x7fOuCEyMkAPgYi | Implement real-time frame classification | GaeU39aVo02Ns60xX1HO8skAIPF9 |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
EUWHVlaneE-7d5wSq5VckMkABMdU | Automatically capture the best READY frame | GaeU39aVo02Ns60xX1HO8skAIPF9 |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
9_Te_HsChUSg7UWfv_do-MkADTGO | Prevent duplicate or incorrect frame captures | GaeU39aVo02Ns60xX1HO8skAIPF9 |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
6FHGU0zlu0GQL3bHEgEoe8kAInsM | Test the system under different conditions | GaeU39aVo02Ns60xX1HO8skAIPF9 |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
SZQdM-ZCfkGq_0rusJNKdMkAMHam | Develop the offline best-frame extractor | F7Ji1x2rDkG_jWrZXmvBnckAEpTj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
_afdUfPwIUmVY3cjABDWf8kAE8kY | Test best-frame extraction using recorded videos | F7Ji1x2rDkG_jWrZXmvBnckAEpTj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
oydZnImbUEWIYh6uiISjSMkAPr0c | Develop the fast manual frame-selection tool | F7Ji1x2rDkG_jWrZXmvBnckAEpTj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
u0I6rIdfCkmDkssIzIz0N8kAB4FH | Process the remaining garment videos | F7Ji1x2rDkG_jWrZXmvBnckAEpTj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
4lNBDMrRIUaTNtLZIclv28kABBkL | Save and verify selected best-frame images | F7Ji1x2rDkG_jWrZXmvBnckAEpTj |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
BSYO4jQmV0KqpCRJFoPHmskAAebg | Prepare and annotate the garment dataset | 5JaaeTRP-Uu3L672Q-snlckAGOIc |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
MLts4swsqkGR4KuPTs84EMkAOFH_ | Train the YOLOv8 garment detection model | 5JaaeTRP-Uu3L672Q-snlckAGOIc |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
NhMGjPjja0Ka37nZfU6cEMkAMR9N | Test the model using sample images | 5JaaeTRP-Uu3L672Q-snlckAGOIc |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
sEgryjfse0CD1dLLtcbEvMkAD7Nl | Improve incorrect or inconsistent detections | 5JaaeTRP-Uu3L672Q-snlckAGOIc |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
jfV1ushJ006U3QQiXQN1Z8kAM8gX | Integrate YOLO with best-frame selection | 5JaaeTRP-Uu3L672Q-snlckAGOIc |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
Abji7WvzrkuAlWjEhf5Gd8kAPgVn | Extract the detected garment mask or contour | h01PgbOWx0miUaDv-eUXx8kAPzWx |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
fqAvksKMY0ySkKgPt3WIVckABp1H | Calculate garment pixel width and height | h01PgbOWx0miUaDv-eUXx8kAPzWx |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
q9C6Vs2YDUqb580DuAUBtckAFidr | Restrict measurement to a single garment | h01PgbOWx0miUaDv-eUXx8kAPzWx |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
o0cNii5VrE2XR4m9Mn7d88kAG5GR | Test measurements for different garment types | h01PgbOWx0miUaDv-eUXx8kAPzWx |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
0FXol0ryaUC_nPTyT-2EPMkAORwV | Prepare the fixed camera calibration setup | dtjLu5o1pUeblLRc5SzpLskAP_jZ |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
1tN6VT3oYUmRJRmlWDqg_8kAACmv | Calculate pixels-per-centimetre values | dtjLu5o1pUeblLRc5SzpLskAP_jZ |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 | 2026-08-04 | 2026-08-04 |  | true
QP4v5JTT1kuxst8rInSpLckANJJI | Calculate pixels-per-centimetre values | dtjLu5o1pUeblLRc5SzpLskAP_jZ |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-31 | 2026-07-28 | 2026-07-28 |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
-B7Ptjqc20KqIezcmcdmHckAOXMQ | Calculate pixels-per-centimetre values | dtjLu5o1pUeblLRc5SzpLskAP_jZ |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-31 | 2026-07-21 | 2026-07-21 |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
S1bwsvuqe0WGhq52m75l9skAIdDL | Calculate pixels-per-centimetre values | dtjLu5o1pUeblLRc5SzpLskAP_jZ |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 | 2026-07-14 | 2026-07-14 |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
U0FeOTuWP0y_1v29d9AFi8kAH9kJ | Convert pixel measurements into centimetres | dtjLu5o1pUeblLRc5SzpLskAP_jZ |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
oaLDU95RcUGLGC1bpZl3dckABCq9 | Validate results using manual measurements | dtjLu5o1pUeblLRc5SzpLskAP_jZ |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
WPrBVsr7f0qjSgL_7rVoZMkADO_1 | Record calibration limitations and measurement errors | dtjLu5o1pUeblLRc5SzpLskAP_jZ |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-25 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
iyzGpCz-ME-ENOdKUHH9z8kAE3Vk | Develop the Next.js camera interface | BrSYHQVpmkKjOKH3Satm-ckABzpq |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
_TOcf6NDEkCt-vFRPbottckABCYx | Connect the frontend with the Python backend | BrSYHQVpmkKjOKH3Satm-ckABzpq |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
X16tiIUffEuksTWCc6mGq8kAKHLi | Integrate best-frame selection and YOLO detection | BrSYHQVpmkKjOKH3Satm-ckABzpq |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
sq9ObM8rd02mbRlG9ehZ2skAGGTz | Display garment width and height in centimetres | BrSYHQVpmkKjOKH3Satm-ckABzpq |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
2IjTAeBi8Ua-hsmgtssyUskAJVbs | Test the complete system workflow | BrSYHQVpmkKjOKH3Satm-ckABzpq |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  | 2026-08-06 |  | false | 2026-08-31 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
Ozq-lFZXuEKnzLe9xNBLkMkAIw00 | Test the system using unseen videos and garments | fJ2OInFrn0iQKXRmhDly5ckAFbjI |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
RBLoYGbMskCFZEmQGIlBXMkAPH4U | Compare automatic and manual measurements | fJ2OInFrn0iQKXRmhDly5ckAFbjI |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
eUd3EfZZU0Oq7_VKOgWeuMkAIgtJ | Record results, errors, and corrective actions | fJ2OInFrn0iQKXRmhDly5ckAFbjI |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
gPDCKCeKFEGwyUKehIFx-MkAPSIw | Prepare the project logbook and documentation | fJ2OInFrn0iQKXRmhDly5ckAFbjI |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
z_qPWqLl-kWYHCVnhJHLlckAKR_H | Prepare the final demonstration and presentation | fJ2OInFrn0iQKXRmhDly5ckAFbjI |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-08-25 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
rRWEy_buMkypnpy71JydRMkAOcmE | Update the research paper with the final component methodology and results. | Ygil0_dRFUyejcayGVlUl8kANo3Y |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
5OuF6oAmuUu9zI08M-mcH8kAOizf | Explain best-frame selection and segmentation-based garment measurement. | Ygil0_dRFUyejcayGVlUl8kANo3Y |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
CuMJSXTDDUaS8w7M3rykxMkAH_t0 | Verify all reported results against saved experiment evidence. | Ygil0_dRFUyejcayGVlUl8kANo3Y |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
czTAI_wkxk6841VxQYJXgMkAJFaN | Record camera calibration assumptions and measurement limitations. | Ygil0_dRFUyejcayGVlUl8kANo3Y |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
yXzoYEUsTEG6LcHV95ZBO8kAGxCu | Prepare the camera-ready paper and required formatting corrections. | Ygil0_dRFUyejcayGVlUl8kANo3Y |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
UbupBtMKlEqENFL3_iEEc8kABjum | Track the conference review outcome and address reviewer feedback. | Ygil0_dRFUyejcayGVlUl8kANo3Y |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
ipsxjKJvmUW7G69qaFjp28kAKfpt | Finalize the individual thesis and check the required formatting. | s05R58ftckW3kS58U8-oeskAMd3k |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false
hQXIcQxUFU2fUklP3rVDvMkACIuB | Update diagrams for frame selection, segmentation and measurement | s05R58ftckW3kS58U8-oeskAMd3k |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false
iQdlUA21bEqHpDAwr5_AnskABjA6 | Prepare the final presentation with verified results | s05R58ftckW3kS58U8-oeskAMd3k |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false
um2PRDQWp0a6_3DBz13IEMkAOmJd | Prepare the live demonstration of garment measurement and counting. | s05R58ftckW3kS58U8-oeskAMd3k |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false
_Q0KNTgGWEOVLA6LUeU5YskAMsuk | Prepare viva answers on model selection, calibration and duplicate prevention. | s05R58ftckW3kS58U8-oeskAMd3k |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false
RdWlbh2Rz0ifRLkMKQ6B6skAM7WQ | Assemble the logbook and component evidence pack. | s05R58ftckW3kS58U8-oeskAMd3k |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false
CPhrvIxu9UyRn2Srh1Idq8kAGmjI | Run a full demonstration rehearsal before the viva | s05R58ftckW3kS58U8-oeskAMd3k |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false
ChRCNfy2GkS4Bx6sKLeRVskAM92i | Record panel feedback and complete the required corrections. | s05R58ftckW3kS58U8-oeskAMd3k |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false
wx_G2IXEt02eU-KEZoeI_skAG7eN | Obtain final supervisor approval. | s05R58ftckW3kS58U8-oeskAMd3k |  | Not started | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false
DpLiVEcCEEytEbGEY_o2pMkABfEh | Define the website requirements for the garment measurement component. | aH9Ng7GYdk2bl0MBZCbd_ckAHcFf |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
Lwsh-Cu27E27dCSDMtg9ockAAnPK | Plan the component pages and website content. | aH9Ng7GYdk2bl0MBZCbd_ckAHcFf |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
2FV5Xfrq30eavB414xLqw8kALT2A | Write the research overview and objectives for best-frame selection and garment size measurement. | aH9Ng7GYdk2bl0MBZCbd_ckAHcFf |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
qEDAcLETU0-KJBd7MWNO0ckAGP1o | Explain the frame-selection, segmentation, calibration and size-estimation methodology. | aH9Ng7GYdk2bl0MBZCbd_ckAHcFf |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
yHTwtDNBjUyhYeCCGsBT6MkAGVaj | Add verified model evaluation and garment measurement results. | aH9Ng7GYdk2bl0MBZCbd_ckAHcFf |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
yKVr4w4wd0uPimAvnvi3fskAExBl | Add component diagrams, interface screenshots and demonstration videos. | aH9Ng7GYdk2bl0MBZCbd_ckAHcFf |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
JHABe6HQCE-93RfhnyjCZskAPYNH | Add report downloads, presentation materials and contributor details. | aH9Ng7GYdk2bl0MBZCbd_ckAHcFf |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82
MM7ptqdhq0mhcfrdVPAHIckAHTK7 | Verify the component pages and links, and support the final website deployment and submission. | aH9Ng7GYdk2bl0MBZCbd_ckAHcFf |  | Completed | Medium |  | 35dfab99-cc9c-48e8-ba44-330bf1c51b82 | 2026-10-14 |  |  |  | false | 2026-10-14 | 35dfab99-cc9c-48e8-ba44-330bf1c51b82

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
fruVw4iDokmybfAdDYQUGMkAMSOy | Project Initiation and Research
BNVOc3FTAUmNvoy3KMkYkMkAMIc0 | Video Collection and Environment Setup
6X9EKxG4pkukMbx5pgSqWckAATLr | Frame Extraction and Annotation
v7nlmZ8DgUWgsGoBM7Jk0ckALUdj | Baseline Image Classifier
jbwNdsAUb0CymkpYS5Kdj8kAK4uE | Failed Experiments and Corrections
X7GIIaR5ck2MlhNCA3ZM5ckAJpLi | Hybrid Model Evaluation
F7Ji1x2rDkG_jWrZXmvBnckAEpTj | Best-Frame Extraction System
GaeU39aVo02Ns60xX1HO8skAIPF9 | Live Camera Best-Frame Selection
5JaaeTRP-Uu3L672Q-snlckAGOIc | YOLO Garment Detection
h01PgbOWx0miUaDv-eUXx8kAPzWx | Garment Pixel Measurement
dtjLu5o1pUeblLRc5SzpLskAP_jZ | Camera Calibration and Centimetre Measurement
BrSYHQVpmkKjOKH3Satm-ckABzpq | Frontend and System Integration
fJ2OInFrn0iQKXRmhDly5ckAFbjI | Testing, Documentation and Finalization
Ygil0_dRFUyejcayGVlUl8kANo3Y | Research Documentation and Publication
s05R58ftckW3kS58U8-oeskAMd3k | Final Report and Viva
aH9Ng7GYdk2bl0MBZCbd_ckAHcFf | Project Website

## Users
User ID | User Name | Email
35dfab99-cc9c-48e8-ba44-330bf1c51b82 | JAYARATHNA W G U C G it22187796 | it22187796@my.sliit.lk