## Plan
Plan ID | Plan name | Date of export
S-dGScRty0-X3edlLqZHnckADY7z | Feature 3-Style and Colour Detection | 2026-10-14

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
NfDmCuWAD0SVIwNULukMhskAHKp5 | Define video data collection requirements | Packing Zone Video Dataset |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-03-31 | 2026-03-25 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 1/1 | Decide what the camera must see at the folding station;Fix video length and framing;Agree the number |  | Scope: overhead footage of the folding and packing zone, roughly three minutes per clip, across several factories.
DxbZVWn_BECDW_zu93jzoskAHvbf | Obtain factory access and recording permission | Packing Zone Video Dataset |  | Completed | Urgent |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-04-08 | 2026-03-30 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 1/1 | Shortlist and contact factories;Send written permission requests;Agree anonymity conditions for work |  | Written permission obtained before any recording. Footage restricted to the packing zone and no worker identification used in the research.
uGfggCJli0OP2FuYoRhA58kAEmqm | Record packing zone video at factory sites | Packing Zone Video Dataset |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-04-21 | 2026-08-06 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Site visit one;Site visit two;Site visit three;Back up all footage |  | Approximately 30 videos of about three minutes each, captured over the folding and packing area.
jYPEpbxDtESz2UkvBMLROskAAn1a | Catalogue and shuffle collected video footage | Packing Zone Video Dataset |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-04-24 | 2026-04-20 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Record source, duration, lighting and line for each clip;Shuffle the video order;Fix the extraction |  | Videos shuffled before extraction so frames from one factory do not cluster into a single split.
_xrmuM009UGMdTweOISmNckAE_-K | Extract frames from the collected videos | Packing Zone Video Dataset |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-04-30 | 2026-04-24 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370
gsJu-_WS-k2o04YVeOZ46MkACM1C | Define the frame annotation schema and state labels | Packing Zone Video Dataset |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-05-01 | 2026-04-27 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Define READY, NOT_READY and INVALID;Write the labelling guideline;Agree the CSV column format;Run a |  | Three-state schema describing the garment on the folding table at the moment the frame was captured.
ERca-cCb2Ei5my2PRI8xWMkADmwK | Annotate extracted frames per video | Packing Zone Video Dataset |  | Completed | Urgent |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-05-15 | 2026-05-04 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Annotate frames video by video;Produce one CSV per video;Spot-check labelling consistency |  | Per-video CSVs let a single video be re-labelled without disturbing the rest of the dataset.
qmlIsp_QM0qgRJDiNyzVM8kAH6e4 | Merge per-video annotations into a single dataset | Packing Zone Video Dataset |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-05-19 | 2026-05-15 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Concatenate all per-video CSVs;Check that frame IDs are unique;Produce the combined dataset file |  | The combined dataset used to train the temporal frame-state model.
J_GtJTG5DUur1cm9BJzFEckAMxSV | Report class distribution across the frame dataset | Packing Zone Video Dataset |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-05-22 | 2026-05-18 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Count samples per state;Compare against a balanced target;Estimate the extra footage a balanced set |  | The READY state occupies only a brief moment in each packing cycle, so uniform frame sampling leaves it badly under-represented. This finding is what later justified withdrawing the temporal model.
BWBzcO95Vk2DfOeHhCi-o8kAICem | Best Frame Capture Logic | Best Frame Capture Logic |  | Completed | Urgent |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-06-09 | 2026-06-05 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | State what a capturable frame must satisfy;List the deterministic signals available per frame;Agree |  | Written after the temporal model was withdrawn. The replacement had to work without a learned frame-state classifier.
fXYTa1r5gEqvp34C32QdUMkAKYNW | Design the layered frame capture gate | Best Frame Capture Logic |  | Completed | Urgent |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-06-12 | 2026-06-08 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Decide the gate ordering;Define every tunable constant;Document why each stage exists |  | A layered deterministic gate: region of interest, then area plausibility, then detection confidence, then blur, then multi-frame consensus. Every stage is inspectable and tunable without retraining.
9sSSF7t3P0O_7pQ6mmtt8ckAFM0o | Implement region of interest cropping | Best Frame Capture Logic |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-06-15 | 2026-06-11 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Implement the ROI crop;Set the horizontal and vertical bounds;Verify against footage from each facto |  | ROI fixed at x from 0.15 to 0.85 and y from 0.20 to 0.95 of the frame, restricting every downstream stage to the folding zone.
xLoPoT7flUuUSknK13NgkMkAOgC4 | Implement blur rejection using variance of Laplacian | Best Frame Capture Logic |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-06-18 | 2026-06-15 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Compute variance of Laplacian per candidate frame;Set the threshold at 8.0;Confirm mid-fold motion f |  | Rejects motion-smeared frames captured while the garment is still being folded.
IAjHqo9umEmvcyc9H-_37MkACntN | Implement box area plausibility checks | Best Frame Capture Logic |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-06-20 | 2026-06-17 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Reject boxes below 15 percent of ROI area;Reject boxes above 85 percent of ROI area;Tune against rec |  | Rejects boxes that are implausibly small, and boxes that swallow the whole region.
FLv48us7pkGhBFJFor8GlskAMDDJ | Implement rolling window capture consensus | Best Frame Capture Logic |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-06-24 | 2026-06-19 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Require two good frames within a four-frame window;Emit one capture per agreement;Test for duplicate |  | Consensus over a short window stops a single lucky frame from triggering a capture.
5xBWotNoXE-VL4TtJQ8_-MkAEnKR | Implement table clear and auto unlock handling | Best Frame Capture Logic |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-06-26 | 2026-06-23 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Detect a cleared table over five frames;Auto unlock after ninety frames;Verify one garment is never |  | Table-state tracking is what prevents the same garment being recorded more than once.
JTcuudLvmUSQlN0BYVxlbskABjHY | Tune capture thresholds against recorded video | Best Frame Capture Logic |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-07-01 | 2026-06-26 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Replay recorded videos through the gate;Compare captures against a manual count;Adjust constants and |  | Confirmed the deterministic gate reaches usable capture behaviour without any learned frame selector.
E3ralW6UkkSQDbFa4QUX7skAPoC7 | Validate capture behaviour during monitoring | Best Frame Capture Logic |  | Completed | Important |  | JAYAWEERA M P Y C it22556370 | 2026-08-26 | 2026-08-14 | 2026-08-03 |  | false | 2026-08-26 | JAYAWEERA M P Y C it22556370 | 0/1 | Observe captures across a live shift;Log missed and duplicate captures;Adjust the ROI for the instal |  | Live validation once the system was installed at the packing station.
IzIr2_0PVEaLPINDKSOBe8kAIE6M | Define garment style detection requirements | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-08-30 | 2026-05-29 | 2026-05-25 |  | false | 2026-08-30 | JAYAWEERA M P Y C it22556370 | 0/1 | Define the four style classes;Decide the framing the detector will see;Set the target dataset size |  | Closed set of four classes: SHIRT, T_SHIRT, SHORT and TROUSER.
p63UkNo7iUGzCA7tBBMfx8kAAiq8 | Collect garment images across the four style classes | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-08-30 | 2026-06-12 | 2026-05-25 |  | false | 2026-08-30 | JAYAWEERA M P Y C it22556370 | 0/1 | Collect images for each style;Check per-class balance;Organise into a working folder |  | Approximately 3,000 garments of differing clothing styles, framed as they appear on the folding table.
CwZKwoZEsU6Ctki40xIdHckAOt49 | Prepare garment style images and annotations | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-08-30 | 2026-06-19 | 2026-06-01 |  | false | 2026-08-30 | JAYAWEERA M P Y C it22556370 | 0/1 | Create the Roboflow project;Draw bounding boxes for 3,033 images;Review annotation consistency;Apply |  | Annotated in Roboflow for versioned datasets and direct YOLO-format export.
-LieepK4Uk-I7kNnjQleNskAFDl0 | Generate the dataset version and train test split | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-08-30 | 2026-06-23 | 2026-06-19 |  | false | 2026-08-30 | JAYAWEERA M P Y C it22556370 | 0/1 | Generate a dataset version;Apply the 70/15/15 split;Export in YOLO format;Record per-class instance |  | Train split contains 2,470 labelled instances: SHIRT 660, SHORT 628, TROUSER 580, T_SHIRT 602.
edy14WS820GI_srqYpy-DMkACbVx | Configure YOLO garment style detection training | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-08-30 | 2026-06-24 | 2026-06-22 |  | false | 2026-08-30 | JAYAWEERA M P Y C it22556370 | 0/1 | Select the YOLOv8n architecture;Set 50 epochs;Fix image size and batch settings;Verify the data conf |  | YOLOv8n chosen for CPU-feasible training and inference on the factory machine.
ZI6x0qgrI0i6hJLi7RYs2skACZHe | Train garment style detection model | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-06-29 | 2026-06-23 |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370 | 0/2 | Run the full training job;Monitor convergence;Export the best weights;Archive results and plots;50 epochs on a CPU-only laptop: 36,214 seconds total, about 10.06 hours, roughly 724 seconds per epo
S-CLyG9sEkCX10G8Zcc36MkAOJi9 | Evaluate garment style detection predictions | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-02 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
pKwcT8CGgkCawUrSChhxTskAHbry | Benchmark garment style inference speed and image size | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-07 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
bhNlh4Ax0kikSHVhG19ZX8kALPSy | Integrate garment style detection with the camera pipeline | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-10 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
IF8uqEM4akqYI0_BcoxWNskAIFMe | Re-run garment style validation on the test split | YOLO Garment Style Detection |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-28 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
bfsXBBZ0SECLSb3zs21uQckAJMga | Implement garment foreground segmentation | Garment Colour Recognition |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-10 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
dH6qK6AQpEqKIyuPFaJI9skAMdZS | Define garment colour recognition requirements | Garment Colour Recognition |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-07 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
h_u9_a0ibUuNNgefo5KpLckADfCa | Implement colour clustering in CIELAB space | Garment Colour Recognition |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-14 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
Hg9BvQmj2EuGjcDLBCzt7MkAC-Jw | Build the reference colour palette and naming | Garment Colour Recognition |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-17 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
i84yHp2t1EKhtze8JKbldckAKkFP | Tune colour cluster retention thresholds | Garment Colour Recognition |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-20 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
Q5QsQkn9kEueHL0C6ebfFckAO-yd | Evaluate colour naming against physical garments | Garment Colour Recognition |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-24 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
D0X1sufeVEidq85EOUa5fskAL7fQ | Integrate colour recognition with the camera pipeline | Garment Colour Recognition |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-27 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
lbTU2b_8B0OFgVVShfqjsckAGoW- | Define monitoring application requirements | Monitoring Application Development |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-03 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
i7zqaNihw0Sd3mFu3zdBEskAEq5k | Set up the Electron and React application shell | Monitoring Application Development |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-06 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
7hEQegB5iUe1eK6QmKi1k8kAENNg | Build the FastAPI backend service | Monitoring Application Development |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-13 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
tZFYutq1uECvXMY26L-sfskAEDOQ | Design the garment record database schema | Monitoring Application Development |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-13 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
UG7IXkNbF0WvKOjPFKcoXMkABGSB | Connect the camera pipeline to the backend | Monitoring Application Development |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-20 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
swCUrGYqMEubHae_DdZ0n8kACaTb | Build the live monitoring dashboard | Monitoring Application Development |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-27 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
jPL9sZxjRUOLsuoFnlE93ckAI9ms | Build order management screens | Monitoring Application Development |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-02 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
rG_xxstb50aGJ8DDZi2kxskANa-w | Build downtime and rework logging screens | Monitoring Application Development |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-04 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
QqCbe8C2bkOqxCRMD2CltckAFWQ1 | Validate end to end capture and storage | Monitoring Application Development |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-08 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
y5vOQ1iOJ0WbpLg0naAp5skAC5XS | Define production analytics requirements | Production Analytics and Forecasting |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-28 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
r3KBZGR60kuBfLaKD8P3NckAEUJH | Implement effective working hours calculation | Production Analytics and Forecasting |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-03 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
tbVz9lepfkiVSxUtsD_cq8kAABYh | Implement packing rate and recent average | Production Analytics and Forecasting |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-05 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
1l_a4oNksEOd-yqiVNjuJckALTZz | Implement order progress and efficiency summary | Production Analytics and Forecasting |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-09 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
Hy8ilzGcvkWLxrPhOvYDmskAIHGs | Implement projected completion and delay estimation | Production Analytics and Forecasting |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-11 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
K6SxpFiF80m1xOcfR5KV8ckACVjw | Implement next day output forecasting | Production Analytics and Forecasting |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-12 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
cOrDJhSsn0eLIqnHXWbruckABTzs | Build the analytics dashboard views | Production Analytics and Forecasting |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-15 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
2SgpE58b90mbP5apjMplSckACZn0 | Validate analytics against recorded production data | Production Analytics and Forecasting |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-18 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
vg7zFJb9Q0Og1I1RkhkjVckAOoax | Define field evaluation requirements | Field Deployment and Evaluation |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-03 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
3oskJRkD9EifildHBPnzXskAKVK4 | Install and align the camera at the packing station | Field Deployment and Evaluation |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-06 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
l2idCMuEtU6P3ekxC43fX8kAIj4q | Run the system across a full production shift | Field Deployment and Evaluation |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-08 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
gCNAhc3-VU6AVRdrjYcrXMkALiLy | Investigate false detections on non garment objects | Field Deployment and Evaluation |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-11 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
Fp1HPR-FOEa6gWc-mzRngMkAGNKR | Raise the detection confidence threshold and re-validate | Field Deployment and Evaluation |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-13 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
uDX4j3TRlkuNG3JYEfEycckAKznr | Document full frame box collapse on wide shots | Field Deployment and Evaluation |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-14 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
EoACpcini0q6iNNXmN53UskAGNbk | Measure capture precision and miss rate | Field Deployment and Evaluation |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-16 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
hJ6eawoR5kKybvMMV3JHV8kALoOP | Extract field trial records from the database | Field Deployment and Evaluation |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-05 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
Kj1r0EVG5UyTrh9BInDSjMkAE9PN | Define the manual counting baseline | Field Deployment and Evaluation |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-14 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
fnFiAdQdwEOz-p7zpNRL98kALheT | Draft the introduction and problem statement | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-07-28 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
74CQ3mWOkUWaokCO1HXW3skAOwoU | Draft the literature review | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-05 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
HCth_beXhEK8AZDYb8FKR8kANQ5E | Draft the methodology chapter | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-14 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
oe7-u_ZwN02uiLfnia30cckAPJHo | Draft the results and evaluation chapter | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-24 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
zJY7Zjkf8E6WU0HPA12LeckAEFFd | Draft the discussion and limitations chapter | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-12 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
YTdOLY3w90OiDVesIX5nIskAO_Ec | Compile references figures and appendices | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-19 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
Ng-sIRFQpEWptLnyH9HBiMkAOaY- | Confirm ICAC 2026 submission requirements | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-27 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
UaxVYe2KP0uuWwK5FRysmskAOKBX | Write the conference paper in the IEEE template | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-30 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
qAtFOs-QlkKOD7UZFo0JxskAHVME | Complete plagiarism check and supervisor review | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-31 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
loeHeqCJcE2ktu-Tmsi0BckAGVZe | Submit the paper to Microsoft CMT | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-01 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
7tzQCu9xR0aMcgsZ-637fMkAPxkI | Archive the submitted paper and its confirmation | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-03 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
uZAcrnDrBkGUygzmVD2aJckAAiNg | Track the ICAC 2026 review outcome | Research Documentation and Publication |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-19 |  |  | false
tf-T9fb96EyK1xRm247H7ckAKCO8 | Compile the technical reference set | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-18 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
OjA1kq0W5kabGoxs8rwrmskAMYT5 | Finalise the thesis after supervisor feedback | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-25 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
1JSWBeNMskquf_wSeXt89MkAGNea | Finalise the draft thesis for the 11 October submission | Research Documentation and Publication |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-11 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
yjaSYxzmR02HC7XZUT9GjMkAIq5R | Prepare the camera-ready plan and timeline | Research Documentation and Publication |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-14 |  |  | false
sH5u8UIrPkWMq8uUVtTbOckAKomc | Define the presentation preparation plan | Final Report and Viva |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-21 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
9Kdf6g8Fv0CBoc3pGIf1UskAD_u_ | Write the presentation speech and slide deck | Final Report and Viva |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-26 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
PXeeuXn_40iwZTHbDtEVsskAADFS | Build the question and answer bank | Final Report and Viva |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-26 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
T1vPJBmXfEKsTAdbwkcwAMkAMXlq | List known weak points and prepare honest answers | Final Report and Viva |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-26 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
omJMkwMWoUO6YK9bXj4QpMkAOR1S | Memorise the figures cheat sheet | Final Report and Viva |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-30 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
n2eumuy_zEO_Ecii8ABPd8kAE6LJ | Rehearse the presentation against the clock | Final Report and Viva |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-30 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
q_yPs4ewHkeJ-WVkVBu498kABLqu | Prepare the live system demonstration | Final Report and Viva |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-08-31 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
p5ckex3MNUeTDcE4NdugjMkANUZ- | Update the presentation for the final viva | Final Report and Viva |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-17 |  |  | false
uz0txDMJwE2rxy0KqTn018kANIf3 | Refresh the question and answer bank with the final results | Final Report and Viva |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-17 |  |  | false
XaZkDs_9wk2K4N6XeMMI5MkAB4my | Assemble the log book and RP evidence pack | Final Report and Viva |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-18 |  |  | false
n3h0QLV_nUKGCCkzgwmqfMkADdi_ | Prepare the final live demonstration | Final Report and Viva |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-18 |  |  | false
4yU-wQG8LkG41YM1zEiMF8kAOrXE | Run a full dress rehearsal before the viva | Final Report and Viva |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-18 |  |  | false
XRyrWVtFCUyBBnt56n86E8kAIqQz | Record panel feedback and required corrections | Final Report and Viva |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-27 |  |  | false
OArHaPuJZU-1t16oacXp9ckAAb9b | Obtain final supervisor sign-off | Final Report and Viva |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-28 |  |  | false
0v_M3xVauE-2tPaWWN_Sw8kADLas | Identify the research problem and domain | Research Proposal and Scoping |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-02-27 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
BkGLHRNT80yvJVR8dZlCw8kADByV | Review related work on garment and apparel vision | Research Proposal and Scoping |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-03-06 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
3Phd4f96jkmiGKtqZH4OGMkAENIL | Define the research objectives and scope | Research Proposal and Scoping |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-03-10 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
ZQeGoVciykOHOXbsS6j8bskAKsdl | Write the research proposal document | Research Proposal and Scoping |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-03-14 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
g3z9u1ZbpEmftFEOCi2ob8kAEFvi | Prepare the proposal presentation | Research Proposal and Scoping |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-03-17 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
uFw_2IwCu0ueF5hM6f5t5MkAKky8 | Incorporate proposal panel feedback | Research Proposal and Scoping |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-03-19 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
3kSTUklUB0etU5sIG9tikskABWhS | Define the project website requirements | Project Website |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-11 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
H4gwlZgfCUabrZJxlibOBMkACyYc | Plan the website structure and content | Project Website |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-15 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
bTvYG0M9uE6AzOtKKLXAHMkAKEm0 | Write the research overview and methodology pages | Project Website |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-22 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
j2w9wz3Wt0KjM4XpHkPBeckABVoh | Prepare figures, screenshots and demonstration media | Project Website |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-18 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
xy81K5byKEWxZfrGyq63X8kAAvwB | Add the results and findings pages | Project Website |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-09-30 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
FLR9BRifbEScLcwPyNGEmckADiRP | Add the documents, downloads and contact pages | Project Website |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-05 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
MGeKyl4-F0aYKDXnmKiIiskAF9PW | Deploy the website and verify every link | Project Website |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-08 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
Gz2CQjs0aU2RYpeBbOnRp8kACRCm | Submit the project website | Project Website |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-13 | 2026-10-11 |  |  | false | 2026-10-13 | JAYAWEERA M P Y C it22556370
6Qb0wvOh1k2pKmgCgCbyQskAA1nR | Submit the research proposal | RP Milestone Submissions |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-03-15 |  |  | false | 2026-10-14 | JAYAWEERA M P Y C it22556370
cEviMhxQa06RtIZbAUuUvskAN0MK | Deliver the proposal presentation | RP Milestone Submissions |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-03-18 |  |  | false | 2026-10-14 | JAYAWEERA M P Y C it22556370
taCF0luAn02Q2VilMUzWP8kAB7O7 | Submit the mid-project check list | RP Milestone Submissions |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-05-13 |  |  | false | 2026-10-14 | JAYAWEERA M P Y C it22556370
l6mwvKkYOEC2lnySVgKhuMkAE6Cv | Deliver Progress Presentation 1 | RP Milestone Submissions |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-05-13 |  |  | false | 2026-10-14 | JAYAWEERA M P Y C it22556370
mwjqb-UVJUu_5848yppE5skANZob | Deliver Progress Presentation 2 | RP Milestone Submissions |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-09-02 |  |  | false | 2026-10-14 | JAYAWEERA M P Y C it22556370
7vQnO-f9YUe9cNwmrCH2fMkAK2ov | Submit the draft thesis | RP Milestone Submissions |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | JAYAWEERA M P Y C it22556370
a5UDlgGLvEOQRoScpr8vzskAHjpo | Submit the final check list | RP Milestone Submissions |  | Completed | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-10-14 |  |  | false | 2026-10-14 | JAYAWEERA M P Y C it22556370
8M6d_8zXOUWG4WXa6bVwaMkAPQX7 | Deliver the final presentation and viva | RP Milestone Submissions |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-10-21 |  |  | false
OrSxaOhtbka_pO6Yd1uXy8kAEUXX | Submit the log book for evaluation | RP Milestone Submissions |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-10-21 |  |  | false
cQ3Lqe-5UUa362I6xjDSRMkAADVq | Submit the research paper | RP Milestone Submissions |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-10-23 |  |  | false
8rffue94iEK54b71FtkAOMkAKM4Y | Submit the final thesis | RP Milestone Submissions |  | Not started | Medium |  | JAYAWEERA M P Y C it22556370 | 2026-10-14 | 2026-10-28 |  |  | false

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
NfDmCuWAD0SVIwNULukMhskAHKp5 | Define video data collection requirements | CB3Tc54CX0WHV-Ddrvk29skAKYWB |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-03-31 | 2026-03-25 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 1/1 | Decide what the camera must see at the folding station;Fix video length and framing;Agree the number |  | Scope: overhead footage of the folding and packing zone, roughly three minutes per clip, across several factories.
DxbZVWn_BECDW_zu93jzoskAHvbf | Obtain factory access and recording permission | CB3Tc54CX0WHV-Ddrvk29skAKYWB |  | Completed | Urgent |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-04-08 | 2026-03-30 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 1/1 | Shortlist and contact factories;Send written permission requests;Agree anonymity conditions for work |  | Written permission obtained before any recording. Footage restricted to the packing zone and no worker identification used in the research.
uGfggCJli0OP2FuYoRhA58kAEmqm | Record packing zone video at factory sites | CB3Tc54CX0WHV-Ddrvk29skAKYWB |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-04-21 | 2026-08-06 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Site visit one;Site visit two;Site visit three;Back up all footage |  | Approximately 30 videos of about three minutes each, captured over the folding and packing area.
jYPEpbxDtESz2UkvBMLROskAAn1a | Catalogue and shuffle collected video footage | CB3Tc54CX0WHV-Ddrvk29skAKYWB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-04-24 | 2026-04-20 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Record source, duration, lighting and line for each clip;Shuffle the video order;Fix the extraction |  | Videos shuffled before extraction so frames from one factory do not cluster into a single split.
_xrmuM009UGMdTweOISmNckAE_-K | Extract frames from the collected videos | CB3Tc54CX0WHV-Ddrvk29skAKYWB |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-04-30 | 2026-04-24 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620
gsJu-_WS-k2o04YVeOZ46MkACM1C | Define the frame annotation schema and state labels | CB3Tc54CX0WHV-Ddrvk29skAKYWB |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-05-01 | 2026-04-27 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Define READY, NOT_READY and INVALID;Write the labelling guideline;Agree the CSV column format;Run a |  | Three-state schema describing the garment on the folding table at the moment the frame was captured.
ERca-cCb2Ei5my2PRI8xWMkADmwK | Annotate extracted frames per video | CB3Tc54CX0WHV-Ddrvk29skAKYWB |  | Completed | Urgent |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-05-15 | 2026-05-04 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Annotate frames video by video;Produce one CSV per video;Spot-check labelling consistency |  | Per-video CSVs let a single video be re-labelled without disturbing the rest of the dataset.
qmlIsp_QM0qgRJDiNyzVM8kAH6e4 | Merge per-video annotations into a single dataset | CB3Tc54CX0WHV-Ddrvk29skAKYWB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-05-19 | 2026-05-15 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Concatenate all per-video CSVs;Check that frame IDs are unique;Produce the combined dataset file |  | The combined dataset used to train the temporal frame-state model.
J_GtJTG5DUur1cm9BJzFEckAMxSV | Report class distribution across the frame dataset | CB3Tc54CX0WHV-Ddrvk29skAKYWB |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-05-22 | 2026-05-18 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Count samples per state;Compare against a balanced target;Estimate the extra footage a balanced set |  | The READY state occupies only a brief moment in each packing cycle, so uniform frame sampling leaves it badly under-represented. This finding is what later justified withdrawing the temporal model.
BWBzcO95Vk2DfOeHhCi-o8kAICem | Best Frame Capture Logic | bCArJ2uRNkuJCUFb_dOzYskAC_U4 |  | Completed | Urgent |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-06-09 | 2026-06-05 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | State what a capturable frame must satisfy;List the deterministic signals available per frame;Agree |  | Written after the temporal model was withdrawn. The replacement had to work without a learned frame-state classifier.
fXYTa1r5gEqvp34C32QdUMkAKYNW | Design the layered frame capture gate | bCArJ2uRNkuJCUFb_dOzYskAC_U4 |  | Completed | Urgent |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-06-12 | 2026-06-08 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Decide the gate ordering;Define every tunable constant;Document why each stage exists |  | A layered deterministic gate: region of interest, then area plausibility, then detection confidence, then blur, then multi-frame consensus. Every stage is inspectable and tunable without retraining.
9sSSF7t3P0O_7pQ6mmtt8ckAFM0o | Implement region of interest cropping | bCArJ2uRNkuJCUFb_dOzYskAC_U4 |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-06-15 | 2026-06-11 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Implement the ROI crop;Set the horizontal and vertical bounds;Verify against footage from each facto |  | ROI fixed at x from 0.15 to 0.85 and y from 0.20 to 0.95 of the frame, restricting every downstream stage to the folding zone.
xLoPoT7flUuUSknK13NgkMkAOgC4 | Implement blur rejection using variance of Laplacian | bCArJ2uRNkuJCUFb_dOzYskAC_U4 |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-06-18 | 2026-06-15 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Compute variance of Laplacian per candidate frame;Set the threshold at 8.0;Confirm mid-fold motion f |  | Rejects motion-smeared frames captured while the garment is still being folded.
IAjHqo9umEmvcyc9H-_37MkACntN | Implement box area plausibility checks | bCArJ2uRNkuJCUFb_dOzYskAC_U4 |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-06-20 | 2026-06-17 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Reject boxes below 15 percent of ROI area;Reject boxes above 85 percent of ROI area;Tune against rec |  | Rejects boxes that are implausibly small, and boxes that swallow the whole region.
FLv48us7pkGhBFJFor8GlskAMDDJ | Implement rolling window capture consensus | bCArJ2uRNkuJCUFb_dOzYskAC_U4 |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-06-24 | 2026-06-19 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Require two good frames within a four-frame window;Emit one capture per agreement;Test for duplicate |  | Consensus over a short window stops a single lucky frame from triggering a capture.
5xBWotNoXE-VL4TtJQ8_-MkAEnKR | Implement table clear and auto unlock handling | bCArJ2uRNkuJCUFb_dOzYskAC_U4 |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-06-26 | 2026-06-23 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Detect a cleared table over five frames;Auto unlock after ninety frames;Verify one garment is never |  | Table-state tracking is what prevents the same garment being recorded more than once.
JTcuudLvmUSQlN0BYVxlbskABjHY | Tune capture thresholds against recorded video | bCArJ2uRNkuJCUFb_dOzYskAC_U4 |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-07-01 | 2026-06-26 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Replay recorded videos through the gate;Compare captures against a manual count;Adjust constants and |  | Confirmed the deterministic gate reaches usable capture behaviour without any learned frame selector.
E3ralW6UkkSQDbFa4QUX7skAPoC7 | Validate capture behaviour during monitoring | bCArJ2uRNkuJCUFb_dOzYskAC_U4 |  | Completed | Important |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-26 | 2026-08-14 | 2026-08-03 |  | false | 2026-08-26 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Observe captures across a live shift;Log missed and duplicate captures;Adjust the ROI for the instal |  | Live validation once the system was installed at the packing station.
IzIr2_0PVEaLPINDKSOBe8kAIE6M | Define garment style detection requirements | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-30 | 2026-05-29 | 2026-05-25 |  | false | 2026-08-30 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Define the four style classes;Decide the framing the detector will see;Set the target dataset size |  | Closed set of four classes: SHIRT, T_SHIRT, SHORT and TROUSER.
p63UkNo7iUGzCA7tBBMfx8kAAiq8 | Collect garment images across the four style classes | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-30 | 2026-06-12 | 2026-05-25 |  | false | 2026-08-30 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Collect images for each style;Check per-class balance;Organise into a working folder |  | Approximately 3,000 garments of differing clothing styles, framed as they appear on the folding table.
CwZKwoZEsU6Ctki40xIdHckAOt49 | Prepare garment style images and annotations | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-30 | 2026-06-19 | 2026-06-01 |  | false | 2026-08-30 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Create the Roboflow project;Draw bounding boxes for 3,033 images;Review annotation consistency;Apply |  | Annotated in Roboflow for versioned datasets and direct YOLO-format export.
-LieepK4Uk-I7kNnjQleNskAFDl0 | Generate the dataset version and train test split | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-30 | 2026-06-23 | 2026-06-19 |  | false | 2026-08-30 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Generate a dataset version;Apply the 70/15/15 split;Export in YOLO format;Record per-class instance |  | Train split contains 2,470 labelled instances: SHIRT 660, SHORT 628, TROUSER 580, T_SHIRT 602.
edy14WS820GI_srqYpy-DMkACbVx | Configure YOLO garment style detection training | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-08-30 | 2026-06-24 | 2026-06-22 |  | false | 2026-08-30 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/1 | Select the YOLOv8n architecture;Set 50 epochs;Fix image size and batch settings;Verify the data conf |  | YOLOv8n chosen for CPU-feasible training and inference on the factory machine.
ZI6x0qgrI0i6hJLi7RYs2skACZHe | Train garment style detection model | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-06-29 | 2026-06-23 |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 0/2 | Run the full training job;Monitor convergence;Export the best weights;Archive results and plots;50 epochs on a CPU-only laptop: 36,214 seconds total, about 10.06 hours, roughly 724 seconds per epo
S-CLyG9sEkCX10G8Zcc36MkAOJi9 | Evaluate garment style detection predictions | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-02 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
pKwcT8CGgkCawUrSChhxTskAHbry | Benchmark garment style inference speed and image size | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-07 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
bhNlh4Ax0kikSHVhG19ZX8kALPSy | Integrate garment style detection with the camera pipeline | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-10 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
IF8uqEM4akqYI0_BcoxWNskAIFMe | Re-run garment style validation on the test split | Qi2GSPWE0Eiy7hwWZt827skAFOPs |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-28 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
bfsXBBZ0SECLSb3zs21uQckAJMga | Implement garment foreground segmentation | C4qlKzDG40u1jM3ZeoHLPckAFfPz |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-10 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
dH6qK6AQpEqKIyuPFaJI9skAMdZS | Define garment colour recognition requirements | C4qlKzDG40u1jM3ZeoHLPckAFfPz |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-07 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
h_u9_a0ibUuNNgefo5KpLckADfCa | Implement colour clustering in CIELAB space | C4qlKzDG40u1jM3ZeoHLPckAFfPz |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-14 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
Hg9BvQmj2EuGjcDLBCzt7MkAC-Jw | Build the reference colour palette and naming | C4qlKzDG40u1jM3ZeoHLPckAFfPz |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-17 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
i84yHp2t1EKhtze8JKbldckAKkFP | Tune colour cluster retention thresholds | C4qlKzDG40u1jM3ZeoHLPckAFfPz |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-20 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
Q5QsQkn9kEueHL0C6ebfFckAO-yd | Evaluate colour naming against physical garments | C4qlKzDG40u1jM3ZeoHLPckAFfPz |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-24 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
D0X1sufeVEidq85EOUa5fskAL7fQ | Integrate colour recognition with the camera pipeline | C4qlKzDG40u1jM3ZeoHLPckAFfPz |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-27 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
lbTU2b_8B0OFgVVShfqjsckAGoW- | Define monitoring application requirements | D9Jgy33ftk6BLKhg8QB7BMkAJGTj |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-03 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
i7zqaNihw0Sd3mFu3zdBEskAEq5k | Set up the Electron and React application shell | D9Jgy33ftk6BLKhg8QB7BMkAJGTj |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-06 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
7hEQegB5iUe1eK6QmKi1k8kAENNg | Build the FastAPI backend service | D9Jgy33ftk6BLKhg8QB7BMkAJGTj |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-13 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
tZFYutq1uECvXMY26L-sfskAEDOQ | Design the garment record database schema | D9Jgy33ftk6BLKhg8QB7BMkAJGTj |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-13 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
UG7IXkNbF0WvKOjPFKcoXMkABGSB | Connect the camera pipeline to the backend | D9Jgy33ftk6BLKhg8QB7BMkAJGTj |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-20 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
swCUrGYqMEubHae_DdZ0n8kACaTb | Build the live monitoring dashboard | D9Jgy33ftk6BLKhg8QB7BMkAJGTj |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-27 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
jPL9sZxjRUOLsuoFnlE93ckAI9ms | Build order management screens | D9Jgy33ftk6BLKhg8QB7BMkAJGTj |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-02 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
rG_xxstb50aGJ8DDZi2kxskANa-w | Build downtime and rework logging screens | D9Jgy33ftk6BLKhg8QB7BMkAJGTj |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-04 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
QqCbe8C2bkOqxCRMD2CltckAFWQ1 | Validate end to end capture and storage | D9Jgy33ftk6BLKhg8QB7BMkAJGTj |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-08 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
y5vOQ1iOJ0WbpLg0naAp5skAC5XS | Define production analytics requirements | wSKuU_Z6akaVvnIBfmtZJskACYNi |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-28 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
r3KBZGR60kuBfLaKD8P3NckAEUJH | Implement effective working hours calculation | wSKuU_Z6akaVvnIBfmtZJskACYNi |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-03 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
tbVz9lepfkiVSxUtsD_cq8kAABYh | Implement packing rate and recent average | wSKuU_Z6akaVvnIBfmtZJskACYNi |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-05 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
1l_a4oNksEOd-yqiVNjuJckALTZz | Implement order progress and efficiency summary | wSKuU_Z6akaVvnIBfmtZJskACYNi |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-09 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
Hy8ilzGcvkWLxrPhOvYDmskAIHGs | Implement projected completion and delay estimation | wSKuU_Z6akaVvnIBfmtZJskACYNi |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-11 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
K6SxpFiF80m1xOcfR5KV8ckACVjw | Implement next day output forecasting | wSKuU_Z6akaVvnIBfmtZJskACYNi |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-12 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
cOrDJhSsn0eLIqnHXWbruckABTzs | Build the analytics dashboard views | wSKuU_Z6akaVvnIBfmtZJskACYNi |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-15 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
2SgpE58b90mbP5apjMplSckACZn0 | Validate analytics against recorded production data | wSKuU_Z6akaVvnIBfmtZJskACYNi |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-18 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
vg7zFJb9Q0Og1I1RkhkjVckAOoax | Define field evaluation requirements | uBZZAwVJxEeBqwYzauwxhMkAJd-J |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-03 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
3oskJRkD9EifildHBPnzXskAKVK4 | Install and align the camera at the packing station | uBZZAwVJxEeBqwYzauwxhMkAJd-J |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-06 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
l2idCMuEtU6P3ekxC43fX8kAIj4q | Run the system across a full production shift | uBZZAwVJxEeBqwYzauwxhMkAJd-J |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-08 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
gCNAhc3-VU6AVRdrjYcrXMkALiLy | Investigate false detections on non garment objects | uBZZAwVJxEeBqwYzauwxhMkAJd-J |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-11 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
Fp1HPR-FOEa6gWc-mzRngMkAGNKR | Raise the detection confidence threshold and re-validate | uBZZAwVJxEeBqwYzauwxhMkAJd-J |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-13 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
uDX4j3TRlkuNG3JYEfEycckAKznr | Document full frame box collapse on wide shots | uBZZAwVJxEeBqwYzauwxhMkAJd-J |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-14 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
EoACpcini0q6iNNXmN53UskAGNbk | Measure capture precision and miss rate | uBZZAwVJxEeBqwYzauwxhMkAJd-J |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-16 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
hJ6eawoR5kKybvMMV3JHV8kALoOP | Extract field trial records from the database | uBZZAwVJxEeBqwYzauwxhMkAJd-J |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-05 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
Kj1r0EVG5UyTrh9BInDSjMkAE9PN | Define the manual counting baseline | uBZZAwVJxEeBqwYzauwxhMkAJd-J |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-14 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
fnFiAdQdwEOz-p7zpNRL98kALheT | Draft the introduction and problem statement | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-07-28 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
74CQ3mWOkUWaokCO1HXW3skAOwoU | Draft the literature review | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-05 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
HCth_beXhEK8AZDYb8FKR8kANQ5E | Draft the methodology chapter | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-14 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
oe7-u_ZwN02uiLfnia30cckAPJHo | Draft the results and evaluation chapter | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-24 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
zJY7Zjkf8E6WU0HPA12LeckAEFFd | Draft the discussion and limitations chapter | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-12 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
YTdOLY3w90OiDVesIX5nIskAO_Ec | Compile references figures and appendices | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-19 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
Ng-sIRFQpEWptLnyH9HBiMkAOaY- | Confirm ICAC 2026 submission requirements | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-27 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
UaxVYe2KP0uuWwK5FRysmskAOKBX | Write the conference paper in the IEEE template | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-30 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
qAtFOs-QlkKOD7UZFo0JxskAHVME | Complete plagiarism check and supervisor review | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-31 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
loeHeqCJcE2ktu-Tmsi0BckAGVZe | Submit the paper to Microsoft CMT | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-01 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
7tzQCu9xR0aMcgsZ-637fMkAPxkI | Archive the submitted paper and its confirmation | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-03 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
uZAcrnDrBkGUygzmVD2aJckAAiNg | Track the ICAC 2026 review outcome | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-19 |  |  | false
tf-T9fb96EyK1xRm247H7ckAKCO8 | Compile the technical reference set | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-18 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
OjA1kq0W5kabGoxs8rwrmskAMYT5 | Finalise the thesis after supervisor feedback | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-25 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
1JSWBeNMskquf_wSeXt89MkAGNea | Finalise the draft thesis for the 11 October submission | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-11 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
yjaSYxzmR02HC7XZUT9GjMkAIq5R | Prepare the camera-ready plan and timeline | jk_A2DmwJE296Nqe-cAfcckAPamP |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-14 |  |  | false
sH5u8UIrPkWMq8uUVtTbOckAKomc | Define the presentation preparation plan | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-21 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
9Kdf6g8Fv0CBoc3pGIf1UskAD_u_ | Write the presentation speech and slide deck | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-26 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
PXeeuXn_40iwZTHbDtEVsskAADFS | Build the question and answer bank | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-26 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
T1vPJBmXfEKsTAdbwkcwAMkAMXlq | List known weak points and prepare honest answers | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-26 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
omJMkwMWoUO6YK9bXj4QpMkAOR1S | Memorise the figures cheat sheet | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-30 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
n2eumuy_zEO_Ecii8ABPd8kAE6LJ | Rehearse the presentation against the clock | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-30 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
q_yPs4ewHkeJ-WVkVBu498kABLqu | Prepare the live system demonstration | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-08-31 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
p5ckex3MNUeTDcE4NdugjMkANUZ- | Update the presentation for the final viva | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-17 |  |  | false
uz0txDMJwE2rxy0KqTn018kANIf3 | Refresh the question and answer bank with the final results | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-17 |  |  | false
XaZkDs_9wk2K4N6XeMMI5MkAB4my | Assemble the log book and RP evidence pack | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-18 |  |  | false
n3h0QLV_nUKGCCkzgwmqfMkADdi_ | Prepare the final live demonstration | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-18 |  |  | false
4yU-wQG8LkG41YM1zEiMF8kAOrXE | Run a full dress rehearsal before the viva | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-18 |  |  | false
XRyrWVtFCUyBBnt56n86E8kAIqQz | Record panel feedback and required corrections | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-27 |  |  | false
OArHaPuJZU-1t16oacXp9ckAAb9b | Obtain final supervisor sign-off | WPg1y_BMAkKgBcAJta99gMkAG4_Z |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-28 |  |  | false
0v_M3xVauE-2tPaWWN_Sw8kADLas | Identify the research problem and domain | ePmbt7q5w0uYjaKRrI1lkMkANB-b |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-02-27 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
BkGLHRNT80yvJVR8dZlCw8kADByV | Review related work on garment and apparel vision | ePmbt7q5w0uYjaKRrI1lkMkANB-b |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-03-06 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
3Phd4f96jkmiGKtqZH4OGMkAENIL | Define the research objectives and scope | ePmbt7q5w0uYjaKRrI1lkMkANB-b |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-03-10 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
ZQeGoVciykOHOXbsS6j8bskAKsdl | Write the research proposal document | ePmbt7q5w0uYjaKRrI1lkMkANB-b |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-03-14 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
g3z9u1ZbpEmftFEOCi2ob8kAEFvi | Prepare the proposal presentation | ePmbt7q5w0uYjaKRrI1lkMkANB-b |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-03-17 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
uFw_2IwCu0ueF5hM6f5t5MkAKky8 | Incorporate proposal panel feedback | ePmbt7q5w0uYjaKRrI1lkMkANB-b |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-03-19 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
3kSTUklUB0etU5sIG9tikskABWhS | Define the project website requirements | gOcr1e8eeUGTsUagk4AbYMkAIvtB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-11 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
H4gwlZgfCUabrZJxlibOBMkACyYc | Plan the website structure and content | gOcr1e8eeUGTsUagk4AbYMkAIvtB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-15 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
bTvYG0M9uE6AzOtKKLXAHMkAKEm0 | Write the research overview and methodology pages | gOcr1e8eeUGTsUagk4AbYMkAIvtB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-22 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
j2w9wz3Wt0KjM4XpHkPBeckABVoh | Prepare figures, screenshots and demonstration media | gOcr1e8eeUGTsUagk4AbYMkAIvtB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-18 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
xy81K5byKEWxZfrGyq63X8kAAvwB | Add the results and findings pages | gOcr1e8eeUGTsUagk4AbYMkAIvtB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-09-30 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
FLR9BRifbEScLcwPyNGEmckADiRP | Add the documents, downloads and contact pages | gOcr1e8eeUGTsUagk4AbYMkAIvtB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-05 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
MGeKyl4-F0aYKDXnmKiIiskAF9PW | Deploy the website and verify every link | gOcr1e8eeUGTsUagk4AbYMkAIvtB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-08 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
Gz2CQjs0aU2RYpeBbOnRp8kACRCm | Submit the project website | gOcr1e8eeUGTsUagk4AbYMkAIvtB |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-13 | 2026-10-11 |  |  | false | 2026-10-13 | b672b8ff-ec1c-4733-b5b7-754a8060a620
6Qb0wvOh1k2pKmgCgCbyQskAA1nR | Submit the research proposal | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-03-15 |  |  | false | 2026-10-14 | b672b8ff-ec1c-4733-b5b7-754a8060a620
cEviMhxQa06RtIZbAUuUvskAN0MK | Deliver the proposal presentation | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-03-18 |  |  | false | 2026-10-14 | b672b8ff-ec1c-4733-b5b7-754a8060a620
taCF0luAn02Q2VilMUzWP8kAB7O7 | Submit the mid-project check list | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-05-13 |  |  | false | 2026-10-14 | b672b8ff-ec1c-4733-b5b7-754a8060a620
l6mwvKkYOEC2lnySVgKhuMkAE6Cv | Deliver Progress Presentation 1 | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-05-13 |  |  | false | 2026-10-14 | b672b8ff-ec1c-4733-b5b7-754a8060a620
mwjqb-UVJUu_5848yppE5skANZob | Deliver Progress Presentation 2 | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-09-02 |  |  | false | 2026-10-14 | b672b8ff-ec1c-4733-b5b7-754a8060a620
7vQnO-f9YUe9cNwmrCH2fMkAK2ov | Submit the draft thesis | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | b672b8ff-ec1c-4733-b5b7-754a8060a620
a5UDlgGLvEOQRoScpr8vzskAHjpo | Submit the final check list | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Completed | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-10-14 |  |  | false | 2026-10-14 | b672b8ff-ec1c-4733-b5b7-754a8060a620
8M6d_8zXOUWG4WXa6bVwaMkAPQX7 | Deliver the final presentation and viva | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-10-21 |  |  | false
OrSxaOhtbka_pO6Yd1uXy8kAEUXX | Submit the log book for evaluation | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-10-21 |  |  | false
cQ3Lqe-5UUa362I6xjDSRMkAADVq | Submit the research paper | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-10-23 |  |  | false
8rffue94iEK54b71FtkAOMkAKM4Y | Submit the final thesis | UUkcAmIn3UKldSwCQJTdVMkAKHVG |  | Not started | Medium |  | b672b8ff-ec1c-4733-b5b7-754a8060a620 | 2026-10-14 | 2026-10-28 |  |  | false

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
CB3Tc54CX0WHV-Ddrvk29skAKYWB | Packing Zone Video Dataset
bCArJ2uRNkuJCUFb_dOzYskAC_U4 | Best Frame Capture Logic
Qi2GSPWE0Eiy7hwWZt827skAFOPs | YOLO Garment Style Detection
C4qlKzDG40u1jM3ZeoHLPckAFfPz | Garment Colour Recognition
D9Jgy33ftk6BLKhg8QB7BMkAJGTj | Monitoring Application Development
wSKuU_Z6akaVvnIBfmtZJskACYNi | Production Analytics and Forecasting
uBZZAwVJxEeBqwYzauwxhMkAJd-J | Field Deployment and Evaluation
jk_A2DmwJE296Nqe-cAfcckAPamP | Research Documentation and Publication
WPg1y_BMAkKgBcAJta99gMkAG4_Z | Final Report and Viva
ePmbt7q5w0uYjaKRrI1lkMkANB-b | Research Proposal and Scoping
gOcr1e8eeUGTsUagk4AbYMkAIvtB | Project Website
UUkcAmIn3UKldSwCQJTdVMkAKHVG | RP Milestone Submissions

## Users
User ID | User Name | Email
b672b8ff-ec1c-4733-b5b7-754a8060a620 | JAYAWEERA M P Y C it22556370 | it22556370@my.sliit.lk