# Project Proposal — Collaboration with MAS Sleekline

Prepared by: Project Team (Computer Vision & IoT)
Date: March 6, 2026

## 1. Executive summary (TL;DR)

We propose a prototype computer-vision + IoT system to automatically count garment pieces, measure cycle time for swing-operators, and classify style / color / size during the quality-check and swing operations. The goal is to replace manual, error-prone logging and an expensive RFID solution with a low-cost webcam prototype plus small IoT switches (ESP32) to mark rework/downtime events. Deliverables: two annotated datasets (quality-check & swing), trained detection/tracking/classification models, edge-capable inference pipeline, ESP32 switch integration, dashboards, and acceptance tests.

## 2. Background & problem statement

Currently quality check staff manually update “good” counts every 15 minutes — a separate task that consumes time and is often missed, producing gaps in data. Swing-machine cycle timing attempts (paddle sensor) fail due to accidental presses. An RFID-based solution is effective but costly. We aim to produce a webcam-based prototype that:

- Automatically detects garment pieces (ignore operator hands).

- Counts pieces & computes cycle time for swing operators.

- Separates good vs rework items and excludes rework/downtime from counts/timings.

- Identifies style (t-shirt, pant, skinny, shirt), color, and predicts size (S/M/L/XL) from measurements.

## 3. Project objectives

Primary

- Build two high-quality datasets (quality-check & swing) covering styles, colors and sizes.

- Implement robust object detection and tracking to count pieces and measure cycle times.

- Integrate ESP32 switches to flag rework and downtime so counts and timings exclude those events.

- Provide a working prototype (camera + inference + dashboard) for factory pilot.

Secondary

- Provide documentation, code, annotated dataset, and a handover package for future scaling (e.g., migrating to RFID or dedicated cameras).

## 4. Scope

### In scope

- Dataset capture plan and dataset creation for:

  - Quality-check process (good vs rework bin placement, style/color/size labels).

  - Swing-operator process (input/output zones, piece detection ignoring hands).

- Object detection, tracking, and classification models (prototype-level, real-time on a local server/edge device).

- Cycle-time calculation for swing operators with configurable input/output zones.

- ESP32-based physical switches for rework and downtime events; integration with inference pipeline.

- Web dashboard: live counts, cycle time stats, style/color distribution, and exportable CSV.

- Acceptance testing at a single production line (pilot).

### Out of scope

- Factory-wide rollout (multiple lines) — can be planned after successful pilot.

- Replacing or retrofitting existing enterprise MIS systems (integration is possible as future phase).

- Full production-grade hardware (industrial cameras) — prototype uses standard webcams.

## 5. Feature breakdown (4 main features)

### Feature 1 — Dataset creation (two datasets)

Goals

- Create two labeled datasets: Quality-Check Dataset and Swing-Operator Dataset.

- Ensure detection of garment pieces while ignoring hand movement.

Coverage & variations

- Styles: t-shirt, pants, skinny, shirt (priority).

- Colors: multiple colors per style (bright, dark, patterned).

- Sizes: labeled by standard size classes and measured dimensions (see Feature 4).

- Lighting: normal factory lighting + a few controlled variations.

- Camera angles: top/oblique and side as needed to optimize detection, but keep setup feasible with existing line rigs.

- Occlusion: partial occlusions, overlapping pieces, operator hands (annotate but not count hands).

Label types

- Bounding boxes for garment pieces.

- Instance IDs for tracking across frames (for cycle time).

- Binary labels for presence of operator hand near the piece (for filtering / augmentation).

- Style, color, size labels (quality dataset).

- Input/output zone annotations (swing dataset).

- Rework / good bin positions (quality dataset).

Dataset size (prototype target)

- Swing dataset: ~6,000–10,000 annotated frames (balanced across styles/colors).

- Quality dataset: ~6,000–10,000 annotated frames plus size-measurement samples (see Feature 4).
(We’ll provide estimates refined during capture.)

### Feature 2 — Count & cycle time

#### 2.1 Swing operator process

- Configure input and output areas (simple rectangular ROIs defined in UI).

- Detect garment instance entering input ROI → start tracking → when it crosses output ROI mark completion and record cycle time.

- Use tracking (SORT/DeepSORT or lightweight tracker) to avoid double counts.

- Exclude frames with heavy operator hand occlusion (use classifier) or when rework/downtime flag is active.

#### 2.2 Quality checker process

- Configure “good” bin and “rework” bin ROIs.

- When a garment is placed into either ROI, increment the corresponding counter.

- When rework flag toggled via ESP32, ensure those pieces are marked and excluded from good-piece counts.

- Downtime toggle (ESP32) pauses cycle-time collection (useful for swing operator).

### Feature 3 — Style & color detection

- From quality-check video crop, run a style classifier (t-shirt/pant/skinny/shirt) and color predictor (dominant color label).

- Output per-piece metadata to dashboard and dataset.

### Feature 4 — Size recognition (dimension → size classification)

- Build a labeled set with measured dimensions per garment sample:

  - Capture standardized photos with a reference ruler or fiducial marker in frame.

  - Measure width/length in pixels and convert to real-world units via calibration (checkerboard or known-sized marker).

  - Map measured dimensions to size labels (S, M, L, XL) based on provided standard measurement table.

- Train a classifier to predict size class from calibrated dimension features and image cues.

## 6. Hardware & IoT integration

- Camera: Industrial-ish USB webcam (1080p, 30 fps) for prototype. Mounting as per capture protocol.

- Edge server: Low-power PC or Jetson-class device for real-time inference (prototype can run on a laptop + GPU).

- ESP32 board(s): Two or three push-button toggles:

  - Rework toggle (on/off)

  - Downtime toggle (on/off)

  - Optional: manual count override

- ESP32 → lightweight MQTT or HTTP API to backend; events are timestamped and used to filter counts/timings.

## 7. Software stack & models

- Data pipeline: OpenCV, FFmpeg for capture; label tool: CVAT or LabelStudio.

- Models:

  - Object detection: YOLOv8 / EfficientDet (prototype) for piece detection.

  - Tracker: ByteTrack / SORT / DeepSORT (lightweight).

  - Classification: small CNN (MobileNetV3) for style/color/size classifier.

  - Post-processing: heuristics to filter hand occlusion and ESP32 flags.

- Backend / API: Node.js or Python (Flask/FastAPI) to ingest stream, run inference, save events.

- Dashboard: simple React/Flutter web UI showing live counts and CSV export.

## 8. Data capture & annotation protocol (practical steps)

- Camera setup: fix camera to stable mount; document distance/angle and capture at factory line height.

- Mark ROIs: physically mark input/output/good/rework zones for annotation consistency.

- Capture sessions: record multiple short sessions (2–10 min) across operators/shifts/styles.

- Annotation rules:

  - Label only garments, not hands; tag frames with hand-presence flag when hand overlaps garment.

  - For swing dataset: annotate when garment crosses input ROI (frame index) and when it crosses output ROI.

  - For quality dataset: label final placement (good/rework) and measurement labels when possible.

- Quality control: sampling-based annotation review (10% checks) to keep label quality high.

## 9. Acceptance criteria & success metrics

- Counting accuracy: ≥ 95% piece-count accuracy for non-edge conditions (pilot target).

- Cycle time measurement: mean error ≤ 10% compared to manual stopwatch in test runs.

- Style classification: ≥ 90% accuracy on held-out test set.

- Size classification: ≥ 85% accuracy for size buckets (prototype target).

- Robustness: Hand-filtering reduces false starts/false stops by ≥ 80% compared to naive counting.

- Latency: End-to-end detection + count update within 1–2 seconds on chosen edge device.

## 10. Timeline & milestones (prototype: 10 weeks — adjustable)

- Week 1 — Kickoff & requirements

  - Onsite measurements, mount locations, ROI definition, sample schedule.

- Weeks 2–4 — Data capture

  - Capture swing & quality videos, annotate initial batch, build labeling pipeline.

- Weeks 5–6 — Model prototyping

  - Train detection & tracker models; implement ROI-based counting logic.

- Week 7 — ESP32 integration

  - Prototype switches, integrate events into pipeline.

- Week 8 — Size measurement calibration

  - Collect measurement-labeled samples and train size model.

- Week 9 — Dashboard & testing

  - UI for live counts, logs, CSV export; run acceptance tests.

- Week 10 — Pilot handover

  - Deliver dataset, code, documentation, and pilot demo at factory.

(If tighter schedule preferred, scope can be split; minimum viable pilot in 6 weeks focusing on counting & ESP32 integration.)

## 11. Risks & mitigations

- Operator hand occlusion causing miscounts

  - Mitigation: hand-presence classifier + ROI logic + conservative tracking heuristics.

- Variable lighting / glare

  - Mitigation: collect diverse lighting samples; use simple normalization & augmentations.

- Camera placement constraints

  - Mitigation: propose multiple mounting options and choose best after a short trial capture.

- ESP32 mis-toggles / human error

  - Mitigation: debounced inputs, audit logs, optional hold-to-toggle behavior.

- Scale-up cost / performance gap

  - Mitigation: prototype to prove feasibility; recommend industrial cameras & edge devices if needed.

## 12. Resource & personnel requirements

- On-site support (from MAS Sleekline):

  - 1 production-line contact for scheduling captures.

  - 1 operator per shift during captures.

  - Physical access for camera mounting and marking ROIs.

- Team (project side):

  - 1 CV engineer (data capture & model training)

  - 1 software engineer (backend + dashboard)

  - 1 IoT/devops (ESP32 + deployment)

  - Optional: 1 annotator (or outsource labeling)

- Equipment (prototype):

  - 2× USB webcams, mounting hardware, laptop/edge device, 2–3 ESP32 dev boards, small LED/labels.

## 13. Estimated budget (prototype-level ballpark)

- Cameras & mounts: USD 200–500

- ESP32 & wiring: USD 30–80

- Edge compute (laptop / Jetson Nano): USD 400–900 (or use existing hardware)

- Labor (10-week prototype): depends on hourly rates — provide quote on request

- Annotation (if outsourced): USD 200–800 depending on dataset size

(We can provide a detailed cost breakdown after confirming factory support & exact dataset targets.)

## 14. Deliverables

- Two annotated datasets (quality-check & swing) and labeling guideline doc.

- Trained detection/tracking/classification models (weights + inference scripts).

- ESP32 firmware and backend event integration.

- Web dashboard with live counts, cycle-time graphs, CSV export.

- Deployment & user manual, and a short demo video of the pilot.

- Final report with metrics, limitations, and next-phase recommendations.

## 15. Acceptance & next steps

If you accept the prototype project, next immediate actions:

- Sign off on scope & pilot line (which production line/shift + contact person).

- Approve initial schedule and designate on-site contact.

- Approve small equipment purchase and camera mounting slot.

- Book first 2 capture days (we'll bring camera + ESP32).

## 16. Appendix A — Capture checklist (quick)

- Camera(s) fixed & stable; recorded resolution & fps logged.

- Input/output/good/rework zones marked physically.

- Reference size marker placed for size measurement frames.

- ESP32 switches mounted near operator line with clear labels.

- Consent from operators for short recording sessions.

## 17. Appendix B — Sample AI prompt (use with internal labelling/model assistant)

"You are a dataset/annotation assistant. Generate a labeling guideline for a factory dataset that contains two contexts: (A) swing-operator process and (B) quality-check process. For each context define object classes, ROI definitions, frame-level event labels (input-cross, output-cross, placed-in-good, placed-in-rework), hand-presence labeling rules, and minimum per-class sample counts. Also provide a short Python validation script that checks annotations for: overlapping IDs, missing ROI timestamps, and size label consistency."

If you want, I’ll convert this into a polished PDF or a one-page executive summary for them. Want that?